## Read Me
Serenity Drug Kits Tracker — WAGPM
Purpose: track WhatsApp business/deal groups Ed is part of as individual
projects — one dashboard per group, each with its own tasks, contacts,
and status updates. Started with the Serenity (South Africa) drug/
screening test kit distribution deal; now also tracking the Botswana
expansion of the same business.
Tabs:
Groups — one row per tracked WhatsApp group
Tasks — one row per action item, linked to a group by name
Status Updates — dated narrative updates per group
Contacts — people involved, by group
Reviewer Notes — annotations/flags added on review
Dashboard — auto-computed totals (formulas only, no manual entry)
Row 5 on each data tab is a kept example row (outside the counted ranges —
delete only if you're sure). Real data starts at row 6.
Groups: rows 6–25 (20 groups)
Tasks: rows 6–59 (54 tasks)
Companion files: index.html (interactive dashboard),
Serenity_Drug_Kits_Tracker_Summary.md (narrative summary). Keep all
three in sync when data changes.

## Groups
Group Name | Aliases | Purpose | Priority | Caution? | WhatsApp Link
Example Group 🌍 | Example | One dense sentence on what's being negotiated. | medium | No | https://chat.whatsapp.com/EXAMPLE
🇿🇦Serenity🇿🇦 | Serenity | Distribution deal for VivaChek drug/screening test kits into South Africa — sourcing via Frank, local commercialization via Nicole (trading as MedSerenity). Critical path is SAHPRA licensing: the full Medical Devices establishment licence requirements arrived 9/25 (5 annexures, R15,600 fee, 6-8 week evaluation); the team is now scheduling a call to assemble and submit the application. | high | No | https://chat.whatsapp.com/LJWJ0UhQQxU6jmBt1q7PXX?mode=gi_t
🇧🇼2026 Botswana Team🇧🇼 | Botswana Team, 2026 Botswana Team | Expanding the same VivaChek drug/screening test kit business (as run in Serenity, South Africa) into Botswana — group stood up 10/13, marketing and pricing materials shared, and a Botswana-specific proposal was reviewed on a call 10/16. | medium | No | https://chat.whatsapp.com/FCASsTy3MrLCW3foimJGr7?mode=gi_t

## Tasks
Group Name | Task | Owner | Status | Notes
Example Group 🌍 | Example task description | Example Owner | In Progress | Example note with date.
🇿🇦Serenity🇿🇦 | Research SADC certificate-of-origin route | Dr. Kudzai Nyamuomba | Done | Raised 8/22; superseded once SAHPRA licensing confirmed required (8/27)
🇿🇦Serenity🇿🇦 | Confirm which regulatory path is required to distribute in SA | Nicole Chitareni | Done | Ministry contact confirmed 8/27: SAHPRA certificate/license still required
🇿🇦Serenity🇿🇦 | Arrange courier of 5 test kits to Nicole | Dr. Kudzai Nyamuomba / Frank | In Progress | Set for 8/26 via The Courier Guy; postponed after Nicole's flu hospitalization (8/25); still no confirmed delivery as of 10/13
🇿🇦Serenity🇿🇦 | Decide which company entity to register/trade under | Nicole Chitareni / Dr. Kudzai Nyamuomba | Done | 8/27: use Nicole's existing CSD-registered company (trading as MedSerenity)
🇿🇦Serenity🇿🇦 | Get SAHPRA compliance quotes | Nicole Chitareni | Done | Two companies quoted 8/27; Pharmers: R55,000 total, R15,600 application-only, ~15 working days
🇿🇦Serenity🇿🇦 | Follow up with Pharmers after slow response | Nicole Chitareni | Done | Follow-up sent 8/31; vendor responded, meeting held 9/8 14:00 CAT
🇿🇦Serenity🇿🇦 | Scope engagement down to application only | Dr. Kudzai Nyamuomba | Done | 9/8: skip consultation and collection-fee add-ons
🇿🇦Serenity🇿🇦 | Visit SAHPRA Radiation Control office in person | ~ Norman Nyamuwomba | Done | Visited Tygervalley office 9/18; told that office doesn't handle test-kit licensing, redirected to SAHPRA Operations Control online
🇿🇦Serenity🇿🇦 | Get Nicole's company details and contact info on file | Dr. Kudzai Nyamuomba | Done | Confirmation letter, AR, tax PIN, and email (poshedluxuryscents@gmail.com) collected 9/17-9/18
🇿🇦Serenity🇿🇦 | Get SAHPRA to confirm the actual licence requirements | ~ Norman Nyamuwomba | Done | SAHPRA's official reply (forwarded 9/25) lists 5 annexures, R15,600 fee, submit to mdadmin@sahpra.org.za, 6-8 week evaluation
🇿🇦Serenity🇿🇦 | Schedule a call to walk through the SAHPRA submission steps | Dr. Kudzai Nyamuomba / Nicole / Norman | In Progress | Requested 9/25; missed 10/3, Nicole traveling 10/5-10/6; as of 10/13 agreed to an after-hours call, not yet confirmed held
🇿🇦Serenity🇿🇦 | Compile and submit the 5-annexure SAHPRA application | Nicole Chitareni / Dr. Kudzai Nyamuomba | Not Started | Blocked on the scheduling call above; no submission yet as of 10/13
🇧🇼2026 Botswana Team🇧🇼 | Introduce team and share initial marketing/pricing materials | Eddie Ed | Done | Product photo, price list, and Serenity marketing brochure shared 10/13
🇧🇼2026 Botswana Team🇧🇼 | Hold kickoff/status call(s) | Dr. Kudzai Nyamuomba / team | In Progress | Held 10/14; a second attempt 10/15 was a 56-sec missed call (Bissau joined); another call held 10/16
🇧🇼2026 Botswana Team🇧🇼 | Share expanded product catalogue (28-panel cup list) | Dr. Kudzai Nyamuomba | Done | 28 Panel Cup List.docx (10pp) shared 10/15
🇧🇼2026 Botswana Team🇧🇼 | Draft Botswana-specific proposal and per-panel pricing | Dr. Kudzai Nyamuomba | Done | Botswana_Drug_Test_Kits docx, Pricing_Per Panel docx, and proposal PDF shared 10/15
🇧🇼2026 Botswana Team🇧🇼 | Review proposal and pricing, align on next steps | Dr. Kudzai Nyamuomba / Eddie Ed / Bissau | In Progress | Discussed on the 10/16 call; outcome not yet captured in the chat

## Status Updates
Group Name | Date | Update
Example Group 🌍 | 1/1/26 | Example status update text.
🇿🇦Serenity🇿🇦 | 9/18/26 | Norman's in-person visit to SAHPRA's Cape Town office found it handles Radiation Control only, not test-kit licensing; redirected online to SAHPRA's Operations Control section (head office Pretoria, office in Durban).
🇿🇦Serenity🇿🇦 | 9/25/26 | SAHPRA confirmed the official Medical Devices establishment licence requirements by email: 5 annexures (cover letter, licence application, Excel form, proof of R15,600 payment, CV, Quality Manual), submitted to mdadmin@sahpra.org.za, 6-8 week evaluation.
🇿🇦Serenity🇿🇦 | 10/13/26 | After a missed call (10/3) and Nicole's travel (10/5-10/6), the team agreed to hold the submission-planning call after work hours to accommodate Norman's schedule; application not yet compiled or submitted.
🇧🇼2026 Botswana Team🇧🇼 | 10/13/26 | New group stood up for the Botswana expansion of the same drug test kit business; initial marketing and pricing materials shared ahead of the first call.
🇧🇼2026 Botswana Team🇧🇼 | 10/16/26 | Botswana-specific proposal and per-panel pricing (shared 10/15) discussed on a call; next steps not yet captured in the chat.

## Contacts
Group Name | Name | Role | Notes
Example Group 🌍 | Example Name | Example Role | Example note.
🇿🇦Serenity🇿🇦 | Dr. Kudzai Nyamuomba | Group organizer / kit sourcing | Coordinates with supplier Frank
🇿🇦Serenity🇿🇦 | Nicole Chitareni | SA local point of contact | Trades as MedSerenity; email poshedluxuryscents@gmail.com
🇿🇦Serenity🇿🇦 | ~ Norman Nyamuwomba | SAHPRA liaison | Visited SAHPRA in person 9/18; got official licence requirements 9/25
🇿🇦Serenity🇿🇦 | Eddie Ed | Group creator
🇧🇼2026 Botswana Team🇧🇼 | Dr. Kudzai Nyamuomba | Group organizer / kit sourcing | Drafted Botswana proposal and pricing
🇧🇼2026 Botswana Team🇧🇼 | Eddie Ed | Group creator / materials | Shared initial marketing and pricing materials
🇧🇼2026 Botswana Team🇧🇼 | Bissau | Team member | Added 10/13; joined calls 10/15

## Reviewer Notes
Group Name | Reviewer | Date | Note
Example Group 🌍 | Example Reviewer | 1/1/26 | Example reviewer note.

## Dashboard
Serenity Drug Kits Tracker — Summary
Metric | Value
Total groups
Total tasks
Tasks done
Tasks in progress
Tasks not started
High priority groups
Medium priority groups
Low priority groups
Groups flagged caution
% tasks done