## Dashboard
WhatsApp Groups Dashboard — Summary
Metric | Value
Total groups
Total tasks
Tasks done
Tasks in progress
Tasks not started
High priority groups
Medium priority groups
Low priority groups
Groups flagged caution
% tasks done

## Read Me
WhatsApp Groups Dashboard — WAGPM
Purpose: track WhatsApp business/deal groups Ed is part of as individual
projects — one dashboard per group, each with its own tasks, contacts,
and status updates.
Tabs:
Groups — one row per tracked WhatsApp group
Tasks — one row per action item, linked to a group by name
Status Updates — dated narrative updates per group
Contacts — people involved, by group
Reviewer Notes — annotations/flags added on review
Dashboard — auto-computed totals (formulas only, no manual entry)
Row 5 on each data tab is a kept example row (outside the counted ranges —
delete only if you're sure). Real data starts at row 6.
Groups: rows 6–25 (20 groups)
Tasks: rows 6–59 (54 tasks)
Companion files: index.html (interactive dashboard), Group_Summaries.md
(narrative summary). Keep all three in sync when data changes.

## Groups
Group Name | Aliases | Purpose | Priority | Caution? | WhatsApp Link
Example Group 🌍 | Example | One dense sentence on what's being negotiated. | medium | No | https://chat.whatsapp.com/EXAMPLE
🇿🇦Serenity🇿🇦 | Serenity | Distribution deal for VivaChek drug/screening test kits into South Africa — sourcing via Frank, local commercialization via Nicole (trading as MedSerenity). Critical path is SAHPRA product licensing; a Cape Town office visit was arranged 9/9 after slow vendor response. | high | No | https://chat.whatsapp.com/LJWJ0UhQQxU6jmBt1q7PXX?mode=gi_t

## Tasks
Group Name | Task | Owner | Status | Notes
Example Group 🌍 | Example task description | Example Owner | In Progress | Example note with date.
🇿🇦Serenity🇿🇦 | Research SADC certificate-of-origin route | Dr. Kudzai Nyamuomba | Done | Raised 8/22; superseded once SAHPRA licensing confirmed required (8/27)
🇿🇦Serenity🇿🇦 | Confirm which regulatory path is required to distribute in SA | Nicole Chitareni | Done | Ministry contact confirmed 8/27: SAHPRA certificate/license still required
🇿🇦Serenity🇿🇦 | Arrange courier of 5 test kits to Nicole | Dr. Kudzai Nyamuomba / Frank | In Progress | Set for 8/26 via The Courier Guy; postponed a week after Nicole's flu hospitalization (8/25)
🇿🇦Serenity🇿🇦 | Decide which company entity to register/trade under | Nicole Chitareni / Dr. Kudzai Nyamuomba | Done | 8/27: use Nicole's existing CSD-registered company (trading as MedSerenity)
🇿🇦Serenity🇿🇦 | Get SAHPRA compliance quotes | Nicole Chitareni | Done | Two companies quoted 8/27; Pharmers: R55,000 total, R15,600 application-only, ~15 working days
🇿🇦Serenity🇿🇦 | Get full cost breakdown reflecting existing ISO 13485/MDSAP certs | Nicole Chitareni | In Progress | Requested 8/27, followed up 8/31, no response yet as of that date
🇿🇦Serenity🇿🇦 | Follow up with Pharmers after slow response | Nicole Chitareni | Done | Follow-up sent 8/31; vendor responded, meeting held 9/8 14:00 CAT
🇿🇦Serenity🇿🇦 | Scope engagement down to application only | Dr. Kudzai Nyamuomba | Done | 9/8: skip consultation and collection-fee add-ons
🇿🇦Serenity🇿🇦 | Visit SAHPRA Radiation Control office in person | ~ Norman Nyamuwomba | In Progress | Requested 9/9 after phone/email went unanswered; Norman confirmed he'd visit Tygervalley office

## Status Updates
Group Name | Date | Update
Example Group 🌍 | 1/1/26 | Example status update text.
🇿🇦Serenity🇿🇦 | 8/27/26 | Ministry confirmed SAHPRA license still required despite SADC certificate; two compliance vendor quotes received same day (Pharmers: R55,000 / R15,600 application-only).
🇿🇦Serenity🇿🇦 | 9/8/26 | Pharmers finally responded after a week of silence; meeting held 14:00 CAT. Team scoped the engagement to application-only.
🇿🇦Serenity🇿🇦 | 9/9/26 | Norman Nyamuwomba (newly added) tasked with an in-person visit to SAHPRA's Cape Town Radiation Control office to get direct answers on process, documentation, and timelines.

## Contacts
Group Name | Name | Role | Notes
Example Group 🌍 | Example Name | Example Role | Example note.
🇿🇦Serenity🇿🇦 | Dr. Kudzai Nyamuomba | Group organizer / kit sourcing | Coordinates with supplier Frank
🇿🇦Serenity🇿🇦 | Nicole Chitareni | SA local point of contact | Based in Louis Trichardt; handles local compliance/logistics; trades as MedSerenity
🇿🇦Serenity🇿🇦 | ~ Norman Nyamuwomba | In-person SAHPRA follow-up | Added 9/8; visiting Cape Town Radiation Control office
🇿🇦Serenity🇿🇦 | Eddie Ed | Group creator

## Reviewer Notes
Group Name | Reviewer | Date | Note
Example Group 🌍 | Example Reviewer | 1/1/26 | Example reviewer note.